## Overview
Local Area Partnership: Overview of the SEND & Inclusion Improvement Programme
Following completion of the previous SEND Strategy, the next phase, 2023 - 2027, has been coproduced with parents/carers, focusing on current issues and future priorities for Oldham’s children and young people with SEND and those who can be considered vulnerable. |  |  |  | Since the inspection, the partnership has:
1) Sought input from DfE and NHSE regional advisors and acted on this to refine the PAP.
Development of the new strategy has taken place during the last year, 2022 - 2023, with consultations taking place in the spring term 2023. The final strategy was approved by cabinet in September 2023. |  |  |  | 2) Held multiple high level meetings with key strategic partners.
3) Held three multi-agency partnership workshops to look at, develop and agree the actions that need to be taken as a partnership.
4) Provided briefings to council members, strategic boards and to the wider SEND system.
The development of the SEND & Inclusion Strategy also coincided with the SEND & Alternative Provision Green Paper, and the Department for Education’s (DfE) proposals for local area partnership plans, which have also been considered in developing the strategy. |  |  |  | 5) Attended follow up meetings with individual service leads to address specific actions.
6) Conducted engagement sessions with system partners and stakeholders by working within and building upon existing communication forums and channels: including with parents, education and health partners.
7) Reviewed and refined the governance systems across the council and the ICP.
Development of the new strategy and underpinning improvement programme also aligns with the Oldham's participation in the Delivering Better Value Programme (DBV), the Change Partnership Programme (CPP), High Needs Provision Capital Allocations Projects (HNPCA) and Early Language Support for Every Child (ELSEC). |  |  |  | 8) Reported formally on SEND at recent cabinet meetings (September 2023), including seeking approval for the SEND & Inclusion Strategy, 2023-2027.
9) Sought Greater Manchester level support and produced a draft ICP Children & Young People's Health Transformation Tracker aligned to the Priority Action Plan, alongside the appointment of a dedicated Child & Young People's Associate Director.
Since the strategy has been drafted, the joint area SEND inspection of the Oldham partnership took place, between Monday 26 June 2023 to Friday 30 June 2023, for which this Priority Action Plan has been developed. |  |  |  | 10) Reviewed the existing SEND & Inclusion Improvement Programme, which underpins the strategy, to ensure that all areas of the inspection letter are represented as areas for improvement within the programme.
The Priority Action Plan sits within a comprehensive SEND & Inclusion Improvement Programme, outlined below, with each priority and infrastructure having a detailed programme of work. Areas for improvement identified in the local area inspection are embedded within the overall programme, aligned with existing actions. The Priority Action Plan is sectioned into two specific priorities (PAP 1 and PAP 2), detailed in the Priority Actions tab, which specifically address the priority areas identified in the inspection report.
SEND & Inclusion Improvement Programme: plan on a page (strategic priorities to be completed by August 2027)
Ref | Priority/enabler | Lead group | Leads | System change | Desired outcome
Priority Action Plan
Priority 1 | Early identification & SEN support | Early Identification & Intervention Partnership | Education: Amber Burton | Work with communities to reduce need, i.e. take a community-centred, preventative approach to delivery of services at the earliest stage to identify and address needs. | There is a consistent approach across the SEND and inclusion system, and this leads to better and more consistent inclusive experiences and more children and young people engaging in education and all areas of life to enable better outcomes.
Health: Agnes Leopald-James
Social Care: Nick Whitbread/Martine Lewis
Priority 2 | Positive health & wellbeing | Children & Young People's Mental Health Steering Group | Education: Vicki Harold | Improve systems that enable earlier identification and classification of social, emotional and mental health (SEMH) needs and underlying needs so that support can be better targeted. | Children and young people who have SEMH needs get the right support, at the right time so they can access all the opportunities available to them.
Health: Gary Flanaghan
Social Care: Nick Whitbread
Priority 3 | Community and social inclusion | PfA Steering Group | Education: Amber Burton | Enable the highest possible level of community involvement for all children and young people, regardless of their needs, in their own local communities. | Children and young people will benefit from remaining an active part of their local community, fostering effective relationships and experiences.
Health: Amara Khan
Social Care: Martine Lewis
Priority 4 | Joint commissioning & sufficiency of specialist support and provision | Joint Commissioning & SEND Sufficiency Partnership | Education: Paula Green | Work across education, health and social care (children's and adults) to identify need and commission specialist support and provision effectively, through joint commissioning. | Children and young people can remain and be successful in local provision, enabling them to take an active part in their own local community.
Health: Angela Welsh
Social Care: Nick Whitbread
Priority 5 | Preparation for adulthood (PfA) | PfA Steering Group | Education: Amber Burton & Amanda Youlden | Improve children and young people’s access to education and support positive transitions into adulthood that leads to better longer-term outcomes. | Children and young people will benefit from a good transition into adulthood, and this will lead to lasting positive outcomes.
Health: Jennifer Rawlins
Social Care: Charlotte Walker
Priority 6a | Communication & interaction: autism | Autism Way Forward Group | Education: Emma Dewar | Secure better outcomes, for children and young people who have autism, that lead to real and productive experiences that are sustainable in their future as adults. | Children and young people who have autism will benefit from effective, targeted support, preventing longer-term needs and over-reliance on services developing.
Health: Heather Martin-Netherwood
Social Care: Charlotte Walker
Priority 6b | Communication & interaction: speech, language & communication needs (SLCN) | SLCN Steering Group | Education: Emma Dewar | Identify the needs of children and young people with speech, language and communication needs (SLCN) at the earliest stage. Develop an enhanced offer at universal, targeted levels to ensure that specialist services are used effectively, for those with the most complex needs. | Children and young people will benefit from effective, targeted support, preventing longer-term needs developing.
Health: Steve Larking & Angela Welsh
Social Care: Nick Whitbread
Enablers
Infrastructure 1 | Engagement, participation and coproduction | Meetings with Barrier Breakers and with POINT/ PCF | Education: Amber Burton | Ensure that the lived experience of children, young people and their families influences strategic plans for SEND and inclusion, leading to change through true coproduction. Use digital technology to enable partners and stakeholders to access support and services or solve problems online, while continuing to provide alternative support and guidance for those who need it. | Children, young people and their families are confident that their voices are heard and drive change at the most fundamental and strategic levels. Full and effective use is made of digital systems and children, young people and their families are empowered to take ownership of their needs as a result.
Health: Angela Welsh
Social Care: Martine Lewis
Infrastructure 2 | Quality assurance and performance | QA & Performance Group | Education: Anthony Shaw & Paula Green | Make every service a good service and every child, young persons and their families experience a good experience. | Children, young people and their families benefit from effective and targeted services that enhance their access to local provision and leads to better outcomes.
Health: Angela Welsh
Social Care: Nick Whitbread & Martine Lewis
Infrastructure 3 | Sustainability (financial balance) | Monthly finance meeting | Education: Paula Green & Amber Burton | Create a sustainable system that has a high level of accountability in relation to the effective use of resources. | Resources are used to the best effect and enable children and young people to achieve the best possible outcomes as a result.
Health: Angela Welsh
Social Care: Nick Whitbread
Infrastructure 4 | Workforce development | Workforce development task & finish group | Education: Vicki Harold & Emma Dewar | Develop and deliver a continuing skills development programme targeting SEND and inclusion to all schools/settings, services, partners and stakeholders. | SEND and inclusion is embedded as part of the natural fabric of local communities, services and provision, enabling all children, young people and their families to flourish.
Health: Angela Welsh
Social Care: Nick Whitbread & Martine Lewis

## Governance
Local Area Partnership: SEND & Inclusion Governance Structure

## Priority Actions
SEND & Inclusion Improvement Programme
Ref | Actions (what we will do) | Owner | Timescale | Success criteria (how we know it's achieved) | Progress (what steps we have taken so far) | Outcome/impact (the difference this made) | Evidence (how we show this) | RAG
Priority area 1: Leaders at Oldham Metropolitan Borough Council and NHS Greater Manchester and Oldham Integrated Care Board should cooperate to urgently improve the shared strategic governance, oversight, support, challenge and planning to deliver effective strategies to meet the needs of children and young people with SEND in Oldham. | [5 empty] | Responsible bodies: Oldham Metropolital Borough Council (OMBC) and NHS Greater Manchester Integrated Care Partnership (GMICP)
Priority area 2: Leaders at Oldham Metropolitan Borough Council and NHS Greater Manchester and Oldham Integrated Care Board, including commissioners and providers, should act urgently to identify and address the delays and gaps in access to health services, especially speech and language therapy, neurodevelopmental pathways and community paediatrics and reduce the negative impact on children and young people with SEND, aged 0 to 25, in Oldham. | [5 empty] | Responsible bodies: NHS Greater Manchester ICB (GMICP)and Oldham Metropolitan Borough Council (OMBC)
PAP: 1.1 | Create Local Inclusion Partnership Executive Board (to sit above Local Inclusion Partnership Board) to ensure higher level accountability and challenge, including: 1. Review and update the ToR. 2. Appoint high level chair/s. 3. Ensure that the DCS, ICP Place Lead or Deputy Place Lead and other senior leadership representation from the LA, ICP, PHE and providers attend and engage in meetings. | Amber Burton & Steve Larking | 2023-09-01 | DCS and ICP Place Based Lead (or deputy place based lead) attend 100% of meetings. Independent Chair, who has extensive SEND system experience, is appointed by end of Dec 2023. | Sep 23: All strategic groups for the partnership are in place for the academic year 23/24. ToR have been updated and submitted for approval at the Sep LIP Executive Board, which has a high level strategic membership who have decision making powers. High level chairs agreed (Harry Catherall, Oldham MBC Chief Executive and Mark Fisher, Chief Executive of NHS Greater Manchester Integrated Care in phase one, to oversee a process to recruit an independent chair, which will begin phase two of the LIP Exec'. Sep 23: High level, nationally recognised independent chair agreed, to commence Jan 2024. | There is high level investment and accountability across the partnership, and this leads to better joint commissioning and decision making. Children, young people and families benefit from improved services as a result. | 1) Membership list and attendance log. 2) Updated ToR. 3) Meeting minutes. 4) Action tracker and risk register.
PAP: 1.2 | Review and agree governance system to ensure appropriate level of support and challenge at all levels. | Steven Larking & Matt Bulmer | 2023-10-01 | Governance system is agreed by key organisations and is in place. | Draft of governance system is complete and is going forward for approval at the Sep 23 LIP Board. Structure has been approved by key partners. | There is confidence across the system that improvements remain high on the agenda for key organisations, and this leads to actions that, in turn, support children, young people and their families. | 1) Structure charts. 2) Papers on consultation and coproduction with parents/carers. 3) Minutes detailing challenge, support and approval.
PAP: 1.3 | Clarify and implement process for each workstream under the SEND & Inclusion Improvement Programme to escalate issues though highlight and challenge reports to the LIP Executive and Partnership Boards, which they can use to challenge progress (alongside KPIs). for resolution, decision making and sign-off. | Amber Burton & Steve Larking | 2023-11-01 | A risk register and highlight/challenge report is in place for all LIP Executive and Partnership Board meetings. | Sep 2023: Highlight and challenge reports discussed at Programme Board and new system agreed and will be circulated to all chairs. | There is regular reporting to the strategic decision makers, and this leads to actions that improve services, ultimately benefitting children, young people and families. | 1) Meeting minutes. 2) Highlight reports. 3) Evidence (in minutes/reports) of robust decisions made because of highlight reports.
PAP: 1.4 | Agree shared protocols for reporting and use of data across the LA and the ICP and implement through a regular cycle of reporting, including NCA providing data monthly, manually collected and reported. | Abi Ajay | 2023-11-01 | Data sharing protocol is in place and data sources and reporting timescales are all identified and provided every month. NCA provide data monthly, manually collected and reported. | Meeting has taken place between LA and ICP commissioners to look at data sharing protocol and next steps. LA has escalated to the CEO of GM ICP that fact that timely performance data in relation to S&LT must be made available. Sep 2023: service level data being shared between NCA and LA. | Data and intelligence will be more joined up, enabling gaps and priorities to be identified and this leads to mitigating actions to address. | 1) Data sharing protocol. 2) Monthly reporting system.
PAP: 1.5 | Review DCO role and strengthen the job description to attract candidates before re-advertising. Liaise with GM partners to explore potential for securing interim DCO capacity until a permanent appointment is made. | Mike Barker & Nicola Hepburn | 2024-01-01 | DCO is in place. | Job description has been reviewed as part of ICP restructure. Interviews and appointments planned for autumn term 2023. | Connections and joint working at the service level is in place, ensuring that services are joined up at the operational level. This benefits children, young people and families as there is improved collaboration between services. | 1) Job description for DCO role. 2) Service structure clearly showing DCO post is filled.
PAP: 1.6 | Ensure joint commissioning arrangements are robust and supported by data, intelligence and insight and use this to develop key priority areas and recommendations to address gaps. This includes revisiting the joint commissioning framework, consideration of pooled budgets, and reviewing and updating the JSNA. | Gerard Jones & Mike Barker | 2024-03-01 | There is an aligned structure for performance reporting measures and metrics to generate key lines of enquiry related to delivery of services through new governance system and potential pooled budgets. A coproduced strategy is in place and embedded, informed by a current JSNA. |  | Improved data and intelligence influences joint commissioning decisions and gaps are targeted as a result. In turn service users have a good experience when accessing support and provision. | 1) Specific data dashboards for commissioned services. 2) SEND data dashboard. 3) Data linked to procurement plans. 4) Reports on recommissioning, evidencing improved specifications.
PAP: 1.7 | Agree a set of outcomes that partners are seeking to achieve together through the services that they commission and strategic actions they take. | Amber Burton & Angela Welsh & Abi Ajay | 2024-04-01 | Updated KPIs have been shared and review of CAMHS outcome framework has been carried out. Outcomes agreed by Barrier Breakers and Oldham PCF have been revisited. All of this results in a high level KPI outcomes framework. | YP Conference planned for December 2023 and will include sign off from young people. This will be used to inform outcomes agreed by partners. | Children and young people's priorities will drive performance for services, and this will lead to a better user experience. | 1) Outcomes framework. 2) KPIs from services (showing alignment to outcomes framework.
PAP: 1.8 | Using IThrive as a model, scope out existing provision of health services with providers and commissioners including alignment with education and early help specialist provision. | Steve Larking & Gary Flanaghan & Angela Welsh | 2024-05-01 | There is clarity about what each service is doing, and roles are clearly understood. IThrive work in partnership (Health) and the graduated response (Education) is in use across the local area. |  | There is more join up across the system for key services leading to children and young people having better access to the support they need. | 1) Report on scope of existing provision.
PAP: 1.9 | Develop a children and young people's health improvement commissioning plan as part of the local partnership transformation work. This will be centred around joint commissioning, integration, contracts and service specs, SLCN, CYP mental health and community paediatrics. | Steve Larking | 2024-06-01 | Plan is in place and clearly details the responsible owner of actions. Closure of escalated issues is at least 30% by March 2024. |  | Clear accountabilities for key services across the system lead to improvements in partnership working and subsequent service delivery. This supports children and young people who benefit from more targeted services. | 1) Health improvement commissioning plan. 2) Service specifications.
PAP: 1.10 | Review and clarify the resources required to meet current needs, including what each partner will contribute, leading to agreeing and implementing contract monitoring arrangements for all health services related to SEND and the S75 agreements (including for 0-19 service). | Gerard Jones & Mike Barker | 2024-06-01 | S75 agreements have been reviewed against requirements to meet current needs and there are revised contract monitoring arrangements in place. |  | Clear accountabilities for key services are included in S75 agreements and leads to improved service specifications. As a result, children and young people benefit from more targeted services. | 1) Section 75 agreements.
PAP: 2.1 | Identify the opportunities to strengthen the early identification and SEN support offer in schools/settings as part of the DfE Delivering Better Value programme and implement this. | Victoria Harold & Amara Khan | 2023-11-01 | DBV final grant bid submitted, outlining plans for SEN support, with delivery taking place over the next 18 months. | Jul 23: Final stage 1 grant bid submitted and approved by DfE. Sep 23: Stage 2 grant bid submitted, and final approval given. All workstreams agreed and focus on early identification, SEN support and transitions. | Delivering Better Value programme will provide 1m of additional funding to conduct support at the early identification and SEN support level. | 1) DBV grant bid. 1) DBV implementation plan. 3) DBV evaluation.
PAP: 2.2 | Audit health and social care partner contributions to education, health and care needs assessment decision making panels for complex cases (including joint commissioning) and agree/ implement new processes that ensure a robust response for all cases. | Paula Green & Nick Whitbread & Steve Larking | 2023-12-01 | A full range of partnership joint commissioning panels are in place which report through joint commissioning governance arrangements. A pathway for joint funding decision making is in place, and 95% of decisions are reached within 2 weeks from original request. | Discussions have been held with key partners and focused sessions planned to look at improvements and next steps. | Joint working and commissioning process improves, through system for gathering better advice that informs decisions. This benefits children and young people with the most complex needs as provision and agreed placements in their EHCPs better reflect their needs. | 1) Audit report. 2) EHCPs. 3) Quality assurance quarterly report.
PAP: 2.3 | Independently review current service delivery to identify the delays and gaps in access to S&LT and make recommendations to the LIP Board about how these should be addressed, including alternative ways of service delivery and the 0-25 range as this bridge’s child and adult services. | Steven Larking | 2024-04-01 | Independent review conducted (linked to GM Balanced System project). Links made with S&LT Lead for GM (Michelle Morris). Full business case for future requirements and recommendations for service delivery of SLCN in Oldham is submitted to the LIP. | The Balanced System work is currently underway. Some data is emerging but not yet available. | There is confidence at the strategic level, that service delivery for S&LT is robust and sustainable. This, in turn, provides a service that children and young people benefit from as they have improved access. | 1) Balanced System reporting. 2) Independent review report on S&LT. 3) Minutes from LIP Executive.
PAP: 2.4 | Evaluate effectiveness of the DBV programme and report recommendations for future sustainability to the LIP Executive, including a costed implementation plan. | Amber Burton | 2025-12-01 | Evaluation report on DBV is submitted to LIP Executive Board, including recommendations and resource implications, for approval. |  | Effective and evidenced based approaches, identified and tested through DBV, are sustained so children, young people and families benefit from an ongoing improved system. | 1) DBV evaluation report.
Speech & Language Therapy: backlog recovery
PAP: 2.5 | Analyse and report on current position of waiting times to include trends in identification, trajectory of demand, key cohorts that need to remain on the list, etc. and use this information as a rescreening tool. | Heather Martin-Netherwood | 2023-10-01 | Monthly monitoring report submitted to LIP Exec Board. | September 2023: Initial meeting with Business Support re data requirements. Service level data shared and needs to be formalised to provide consistency for monitoring system. Summary report prepared for LIP Exec Board in Oct. | There is a better understanding of the existing waiting list, and this can be used to identify improvements which result in a better support offer for children, young people and families. | 1) Data analysis of existing waiting list. 2) Monthly data report.
PAP: 2.6 | Agree numbers of new referrals to be seen to start to reduce the waiting list and align this with performance measures for contract monitoring purposes. | Steve Larking & Heather Martin-Netherwood | 2023-11-01 | Agreed plan in place, including staffing resource required, with timescales for reduction of waiting list. | Waiting list cleanse and validation for preschool age has been completed and is in process for school age. Waiting well resources have been produced and are sent out to parents/carers of children on the waiting list. Summary report prepared for LIP Exec Board in Oct (linked with 2.5). | There is a reduction in waiting times so children and young people benefit from more timely access to services that enable them to have their needs met earlier. | 1) Monthly reporting.
PAP: 2.7 | Produce a detailed S&LT waiting list recovery plan and agree this through the LIP Executive Board. | Kate McKenna & Heather Martin-Netherwood | 2023-11-01 | S&LT waiting list recovery plan is in place and being implemented. This leads to a reduction in waiting times. Target 50% reduction by Sep 2024. | Actions taken to cleanse the S&LT waiting list. All schools contacted. S&LT waiting list recovery plan has been drafted and some actions taking place in anticipation of approval. | Children and young people have their needs identified and met at the earliest opportunity. | 1) S&LT waiting list recovery plan. 2) Data dashboard related to recovery plan.
PAP: 2.8 | Agree protocol for S&LT response to education, health and care needs assessment requests to ensure appropriate level of assessment of need is contributed within six weeks of notification/request for information. | Heather Martin-Netherwood & Paula Green | 2023-11-01 | 95% of assessment of need for S&LT contribution to EHCP is completed and provided within 6 weeks, by April 2024. 100% of assessment of need for S&LT contribution to EHCPs is completed and provided within 6 weeks by September 2024. | Sep 23: Work between key services has begun and further task and finish groups planned. | Quality and timeliness of advice for the EHC needs assessment process improves, leading to better quality EHCPs that accurately reflect the needs and provision for children and young people. | 1) Protocol agreement. 2) QA of EHCP audit reports.
PAP: 2.9 | Scope out the potential requirement for use of the independent sector to support waiting list backlog recovery. | Nicola Hepburn | 2023-12-01 | Scoping exercise has taken place and reports to LIP Executive. SLA is in place with an independent sector provider, to increase capacity by +500 hours of clinical time. |  | There is improved capacity to support reduction in waiting times so children and young people benefit from earlier support. | 1) Scoping report.
PAP: 2.10 | Reduce the numbers of children and young people on the waiting list for S&LT services from the August 2023 figures of 992 mainstream/399 complex/114 clinic: | Kate McKenna & Heather Martin-Netherwood | 2024-09-01 | By April 2024, -100 for mainstream/-100 for complex needs. By September 2024: -200 for mainstream/-200 for complex needs. Target 20% reduction of S&LT waiting list by April 2024 and a 50% reduction by September 2024). |  | There is a bigger reduction in waiting times and the trajectory shows this is continual so gains made to address waiting lists are sustained. Children and young people benefit from more timely access to services that enable them to have their needs met earlier. | 1) Monthly reporting. 2) Reports to LIP Executive and Partnership Boards.
Speech & Language Therapy: sustainability
PAP: 2.11 | In partnership with the SEND & Inclusion Service, review the training offer for SENCos and strengthen the offer for SLCN to improve workforce development. | Heather Martin-Netherwood & Emma Dewar | 2023-12-01 | A coproduced SLCN training offer from across education and health services is rolled out. | Intel gathering has begun regarding training offers available plus service support for SENCos/school staff. Via the RSA workstream, a document is being compiled that details service offers available to educational settings. Intel gathering has begun regarding training offers available across services. | Children and young people will be supported by professionals who better understand their needs and the provision they require and as a result will be supported to achieve improved outcomes. | 1) SLCN training offer to schools/settings.
PAP: 2.12 | Agree, through partnership working as part of the DfE Change Programme Partnership, implementation of the ELSEC programme. | Angela Welsh & Amber Burton | 2023-12-01 | ELSEC programme planned and implementation stage beginning. | Initial meetings held to discuss ELSEC, which has been allocated to Oldham as part of the Change Programme. | Children in primary schools will have access to more support for early language, ensuring they have their needs met at the earliest stage. | 1) ELSEC implementation plan. 2) Change Programme Steering Group minutes.
PAP: 2.13 | Review and identify the workforce and resources required, over the next five years, to meet the needs of children with complex SLCN who are referred into the core S&LT service. | Heather Martin-Netherwood | 2024-02-01 | An analysis document and briefing note has been completed which details the required staffing resource for current and future needs. This is presented to both the LIP and the Joint Executive for Commissioning. | Revised referral form, acceptance criteria and clinical triage process are in place to ensure that only those children whose needs require input from S&LT are accepted into the service. | Children and young people will have access to support from a more enhanced workforce regarding early language, ensuring they have their needs identified and met at the earliest stage. | 1) ELSEC implementation plan. 2) Change Programme Steering Group minutes. 3) SENCo development days.
PAP: 2.14 | With SEND & Inclusion Service, promote/embed the Speech, Language and Communication Framework (SLCF) to support universal identification and intervention for speech, language and communication needs (SLCN). | Heather Martin-Netherwood & Emma Dewar | 2024-05-01 | SLCF and Total Communication Policy is used and embedded within >60% primary school settings. Regular monitoring of use is promoted at SENCo Development Days and networking events. | Promote/share the SLCF at upcoming SENCo Development Day (Sep 23) alongside the updated Total Communication Policy. Total Communication Policy to be presented by the S&LT Service on 8/11/23 at a SENCO Development Day. | Using the SLCF, education practitioners will be able to identify and appropriately support universal speech, language and communication needs so that children and young people benefit from improved understanding of universal provision in schools and settings. | 1) SENCo development day plans. 2) SLCF take up by SENCos with monitoring through QEST. 3) Total Communication Policy.
PAP: 2.15 | Scope out and explore joint commissioning of either Primary WellComm or SpeechLink and LanguageLink to address the gap re the Universal and Targeted offer for SLCN in schools, including screening and interventions as part of the tool. | Heather Martin-Netherwood & Emma Dewar | 2024-05-01 | Programmes have been collaboratively reviewed and then agreement made on standardised tools to be commissioned/promoted within educational settings. | Secondary Language Link commissioned for all LA maintained and academy secondary schools from Sep 23. Primary Wellcomm established in most primary schools. Better Communication Team and LA advisory roles recommend and support use within primary settings. Quote received for Infant and Junior Language Link for all maintained and academy primary schools. Primary WellComm is being used in some Oldham primary schools. The Better Communication Team and Health and Education services recommend and support the use of this tool within primary and early years settings. | Through standardised assessment tools, education practitioners identify and support universal and targeted levels of SLCN within the education setting, leading to more accurate identification of those to be referred to S&LT. In turn this will lead to a reduction in the numbers on the S&LT waiting list. | 1) Commissioning agreements. 2) S&LT waiting list. 3) Screening tools evaluation.
PAP: 2.16 | Review impact of ELSEC programme and make recommendations for sustainability, using evidenced based evaluation to inform decision making. | Angela Welsh & Amber Burton | 2024-07-01 | Formal review of ELSEC has taken place and recommendations taken forward into the sustainability stage for ongoing support and provision. |  | Key benefits from the ELSEC programme have been identified and established on an ongoing basis and this benefits children in primary schools as their support needs are identified and addressed. | 1) ELSEC evaluation. 2) Proposal for ongoing sustainability of key success outcomes.
Community Paediatrics
PAP: 2.17 | Develop proposal for sleep pathway. | Catherine Fox & Angela Welsh | 2023-11-01 | Proposal finalised and taken through system governance. | Task & finish group has been set up to develop proposal. Engagement from wider stakeholders to inform development. | Families have access to community sleep support. Further reductions seen in spend on sleep medication Reduction in demand for community paediatrics. | 1) Meeting minutes. 2) Medicines optimisation data. 3) Community paediatrics activity data.
PAP: 2.18 | Conduct waiting list cleanse to reduce wasted appointment slots. | Catherine Fox | 2024-11-01 | Waiting list is a true reflection of demand and there is a reduction in wasted slots. | Secretaries contacting new patients due an appointment within the next month to determine appointment still required. | Families have access to community paediatric services with shorter waiting times. | 1) Waiting lists and data.
PAP: 2.19 | Plan meetings with partners and stakeholders to support knowledge and understanding of services resulting in a reduction in inappropriate referrals. | Catherine Fox | 2023-12-01 | Re-audit of triage outcomes shows increase in appropriate referrals to the service | Dr Shipp scheduled to attend SENCo forum to update on expectations of service in November 2023. Requested meeting slot on GP forum. | Families have confidence in services as they see their views considered for improvements. | 1) Meeting minutes. 2) Briefings and communications.
PAP: 2.20 | Review triage outcome letter to identify advice and signposting to be included. | Catherine Fox | 2023-12-01 | Families are provided with signposting and advice to support them whilst awaiting an appointment with community paediatric service. | Taken up acknowledgement letter devised and shared in the team and with POINT for comments. | Families have access to the right information regarding community paediatric services and this leads to more confidence in the system. | 1) Triage letters and comms. 2) Online information about community paediatrics.
PAP: 2.21 | Review transition between children's and adults’ services and, where gaps are identified, include recommendations, to be approved at LIP Executive Board, to address these. | Catherine Fox | 2024-06-01 | Audit YP (14+) transferred to GP/transition to adult service plan in place. | Dr Howard attending regular transitions meetings including GM level to ensure effective transition for children. Transitions framework shared with all community paediatric team with approval to embed in practice. | Reduction in parental concerns incident reported due to waiting for an appointment | 1) Report on the review into transition between services. 2) LIP Executive Board minutes.
PAP: 2.22 | Improve capacity within the service to recover long wait times. | Catherine Fox | 2024-07-01 | Review of medics’ clinic templates to increase new patient slots has been conducted and ND Nurse clinics are in place to assess new patients 5yrs+ on the ASC pathway. Data results of true waiting times reflect evidence of prioritisation for those with high need/risk. There is a reduction in waiting times as a result. | Neurodevelopmental patients transferred to nurse clinics for diagnostic feedback and follow up. Additional clinical sessions planned in addition to current job plan to support waiting list. | Stratification to ensure correct age groups are seen by the correct team (developmental phase to paediatrics, older age review with CAMHS) means that waiting times reduce and more appropriate decisions are made. These benefit individuals who require services through earlier identification leading to support being better targeted. | 1) Data re: waiting lists. 2) Templates for clinics. 3) Pathways maps. 4) Analysis of results from questionnaires.
Neurodevelopmental pathways
PAP: 2.23 | Implement updated pathway between Community Paediatrics (age 7 and below) and CAMHS (age 8 and over) to ensure seamless approach and eliminate duplication. | Gary Flanagan | 2023-11-01 | Clear guidance for partners regarding which service to refer to, dependant on YP’s age at presentation, is agreed and disseminated. There are reduced numbers of cases requiring additional discussion between CAMHS and Community Peads leadership team. | Referrals being forwarded to correct service for assessment. To be reviewed in April to see service impact. | Clear guidance for referrers means that more appropriate referrals are made, resulting in more targeted support and intervention at the earliest opportunity. | 1) Pathways maps. 2) Guidance re: pathways. 3) SENCo development days (agenda and evaluations).
PAP: 2.24 | Development of ICB Greater Manchester plan for 18+ pathway. | Gary Flanagan | 2023-11-01 | Report finalised and presented to ICP Board. | DRAFT has been provided for ICB boards in Sep 23 (timescales to be determined following board meetings). | Agreed GM pathway for ASD/ADHD 18+ ensures there is consistency across GM. | 1) Evaluation report of agreed provider.
PAP: 2.25 | Review transition between children's and adults’ neurodevelopmental services and, where gaps are identified, report to LIP Board with recommendations to address these. | Gary Flanagan & Angela Welsh | 2023-11-01 | Report and recommendations submitted to LIP Board in November 2023. | Currently post 16 assessments are conducted by Optimize. CAMHS ND cases are transitioned to Optimise at age 16. | Improve transition experience for our YP in service. | 1) Report on ND services, identifying gaps in provision. 2) LIP Executive Board minutes.
PAP: 2.26 | Review and identify increased capacity requirements in community paediatrics to support waiting times. Use this to inform future commissioning. | Catherine Fox & Angela Welsh | 2023-12-01 | Capacity requirements in community paediatrics to support waiting times have been reviewed and report produced, including recommendations, and reported to LIP Executive Board. |  | Better informed commissioning means that more appropriate levels of service are commissioned. Children and young people benefit as a result, as they have better access to services. | 1) Report on capacity of community paediatrics. 2) LIP Executive Board minutes.
PAP: 2.27 | Improve the quality of referrals through partnership approaches such as mutual aid to identify and implement more joined up working to ensure better referrals across the system. | Sarah Leah & Catherine Fox | 2023-12-01 | Referral processes and pathways are clear and accessible in the most appropriate way for service users. New referral forms are launched in collaboration with POINT. | Once finalised Community Peads and CAMHS to advise referrers, including schools and GP surgeries of the referral pathways. This will occur after review of process in April 2024 | There is improved patient experience and this builds confidence of users as their needs are identified and there is a joined up approach to support. | 1) Data showing reduction in signposting of referrals. 2) Minutes from partnership meetings. 3) Feedback from users.
PAP: 2.28 | Launch revised pathways approach with external partners at a high profile SEND & Inclusion conference aimed at headteachers and partners. | Gary Flanagan & Emma Dewar | 2023-12-01 | Revised pathways agreed and launched at SEND & Inclusion conference (SEND sector and parents/carers). | Opportunities to launch at: Headteachers and partners conference (provisional date 28 November 2023). Currently piloting new criteria with regards to community peadiatrics and CAMHS. Review April 2024 to see how this process is working and then cascade information to referrers. | Better informed leaders mean that more appropriate referrals are made into the correct pathway. | 1) Pathways maps.
PAP: 2.29 | Undertake review of the updated ND pathway at 6 months. | Sarah Leah & Catherine Fox | 2024-03-01 | Review of ND pathway at six months has been conducted and reported, including recommendations for improvements to LIP Board. |  | Improvements are made to the ND pathway and service users have their needs identified earlier, leading to better outcomes. | 1) Report on review of ND pathways at six months to LIP Executive Board. 2) Pathways maps.
PAP: 2.30 | Mobilise comprehensive CAMHS in Oldham, addressing commissioning gaps for 16-18y. | Gary Flanagan & Sarah Leah | 2024-05-01 | Commissioning gaps for CAMHS have been identified and recommendations made to LIP Board. | In process of recruiting to posts to provide comprehensive CAMHS service. Recruitment remains an issue at present nationwide | Young people are assessed by appropriate services, resulting in confidence in the system. | 1) Staffing structures showing vacant posts filled 2) Pathway maps.
Complete: Action fully completed and intended impact/outcome is evident.
On track: The action has started, is on track for completion, and there are no issues raised requiring escalation.
Vulnerable: Action looks unlikely to be achieved, or timescales met, as planned and this may have implications on improvements, so requires escalation.
At risk: There is a risk that this action will not be completedand escalation is required and a plan to mitigate risks must be implemented.
Not yet started: The action is planned as part of expected delivery timescales but is not yet due and/or is dependent on preceeding actions.

## Partners 23-24
SEND & Inclusion Improvement Programme: local area partners and stakeholders
Name | Role/organisation | Contact | Group
1: Local Inclusion Partnership Executive Board
Harry Catherall: Chair | Chief Executive Officer, OMBC | harry.catherall@oldham.gov.uk | LIP EB
Mark Fisher: Chair | Chief Executive Officer, Greater Manchester Integrated Care Partnership | mike.barker3@nhs.net | LIP EB
Amber Burton | Assistant Director, SEND & Inclusion, OMBC | amber.burton@oldham.gov.uk | LIP EB
Andrew Robinson | Chief Executive Officer, POINT | andrew@point-send.co.uk | LIP EB
Gerard Jones | Managing Director Children’s Services, OMBC | gerard.jones@oldham.gov.uk | LIP EB
Julie Daniels | Director of Childrens Social Care, OMBC | julie.daniels@oldham.gov.uk | LIP EB
Matthew Bulmer | Director of Education, Skills & Early Years, OMBC | matthew.bulmer@oldham.gov.uk | LIP EB
Mike Barker | Place Lead, Oldham & NHS Greater Manchester Integrated Care Partnership | mike.barker3@nhs.net | LIP EB
Nicola Hepburn | Director of Delivery & Transformation/Deputy Place Lead (Oldham), NHS Greater Manchester IICP | nicola.hepburn1@nhs.net | LIP EB
Steve Larking | Associate Director: Children and Young People (Transformation), Integrated Care Partnership (Oldham) | s.larking@nhs.net | LIP EB
Steve Larking | Associate Director: Children and Young People (Transformation), Integrated Care Partnership (Oldham) | s.larking@nhs.net | LIP EB
2: SEND & Inclusion Programme Board
Andrew Robinson: Chair | Chief Executive Officer, POINT | andrew@point-send.co.uk | SEND&I PgB
Amber Burton: 2nd Chair | Assistant Director, SEND & Inclusion, OMBC | amber.burton@oldham.gov.uk | SEND&I PgB
Amaara Khan | Directorate Manager Oldham Integrated Children’s Community Services Ages 0 - 19 | amaara.khan@nca.nhs.uk | SEND&I PgB
Amanda Youlden | Post 16 Lead, OMBC | amanda.youlden@oldham.gov.uk | SEND&I PgB
Andrea Greenwood | Oldham Parent Carer Forum Development Manager, POINT | andrea@point-send.co.uk | SEND&I PgB
Angela Welsh | Senior Commissioning Business Partner, NHS Greater Manchester Integrated Care | a.welsh@nhs.net | SEND&I PgB
Anthony Shaw | SEND Team Manager, OMBC | anthony.shaw@oldham.gov.uk | SEND&I PgB
Daniel Powner | Head of Adults Learming Disabilities, Autism & Mental Health | daniel.powner@oldham.gov.uk | SEND&I PgB
Gary Flanagan | Strategic Lead for Mental Health Crisis & Liaison (GM) & Mental Health and Learning Disability (Oldham) | gary.flanagan@nhs.net | SEND&I PgB
Gavin Lyons | Executive Headteacher, Newbridge School | glyons@newbridgegroup.org | SEND&I PgB
Heather Martin-Netherwood | Associate Director, Children’s Community Services, Northern Care Alliance (NCA) | heather.martinnetherwood@nca.nhs.uk | SEND&I PgB
Martine Lewis | Head of Service, Disabled Children’s’ Team, OMBC | martine.lewis@oldham.gov.uk | SEND&I PgB
Paula Green | Head of Service, SEND and Inclusion, OMBC | paula.green@oldham.gov.uk | SEND&I PgB
Paula Healey | Head of Early Years, OMBC | paula.healey@oldham.gov.uk | SEND&I PgB
Steve Larking | Associate Director: Children and Young People (Transformation), Integrated Care Partnership (Oldham) | s.larking@nhs.net | SEND&I PgB
Vicki Harold | Principal Educational Psychologist & Preventative Lead, OMBC | victoria.harold@oldham.gov.uk | SEND&I PgB
3: Quality Assurance & Performance Group
Paula Green: Chair | Head of Service, SEND & Inclusion, OMBC | paula.green@oldham.gov.uk | QA&P Grp
Martine Lewis: 2nd Chair | Head of Service, Disabled Children’s’ Team, OMBC | martine.lewis@oldham.gov.uk | QA&P Grp
Andrea Greenwood | Oldham Parent Carer Forum Development Manager, POINT | andrea@point-send.co.uk | QA&P Grp
Andrew Evans | SEND Finance & Admin Manager, OMBC | andrew.evans@oldham.gov.uk | QA&P Grp
Andrew Robinson | Chief Executive Officer, POINT | andrew@point-send.co.uk | QA&P Grp
Angela Welsh | Senior Commissioning Business Partner, NHS Greater Manchester Integrated Care | a.welsh@nhs.net | QA&P Grp
Anthony Shaw | SEND Team Manager, OMBC | anthony.shaw@oldham.gov.uk | QA&P Grp
Catherine Fox | Assistant Directorate Manager, Community Paediatric Service | catherine.fox@nca.nhs.uk | QA&P Grp
John Gilmore | Senior Intelligence & Data Analyst | John.gilmore@oldham.gov.uk | QA&P Grp
Martin Burroughs | Intelligence & Data Business Partner, OMBC | martin.burroughs@oldham.gov.uk | QA&P Grp
Sarah Bell | Project Manager, OMBC | sarah.bell2@oldham.gov.uk | QA&P Grp
Vicki Harold | Principal Educational Psychologist & Preventative Lead, OMBC | victoria.harold@oldham.gov.uk | QA&P Grp
4: Local Inclusion Partnership Board
Cllr Mohon Ali: Chair | Lead Member for Education & Skills, OMBC | mohon.ali@oldham.gov.uk | LIP PB
Andrew Robinson: 2nd Chair | Chief Executive Officer, POINT | andrew@point-send.co.uk | LIP PB
Adam Shipp | Clinical Director, Community Paediatrics, Northern Care Alliance (NCA) | adam.shipp@nca.nhs.uk | LIP PB
Agnes Leopald-James | Assistant Director, Childrens Community Nursing, Northern Care Alliance (NCA) | agnes.leopold-james@nca.nhs.uk | LIP PB
Alan Benvie | Assistant Principal FE, Oldham College | alan.benvie@oldham.ac.uk | LIP PB
Amber Burton | Assistant Director, SEND & Inclusion, OMBC | amber.burton@oldham.gov.uk | LIP PB
Andrea Greenwood | Oldham Parent Carer Forum Development Manager, POINT | andrea@point-send.co.uk | LIP PB
Andrea Weir | Senior Commissioning & Partnerships Manager, OMBC | andrea.weir@oldham.gov.uk | LIP PB
Chris Lewis | Youth Service OMBC | chris.lewis@oldham.gov.uk | LIP PB
Claire Smith | Director of Nursing & Quality NHS | claire.smith23@nhs.net | LIP PB
Cllr U Nasheen | Deputy Lead Member, OMBC | u.n@oldham.gov.uk | LIP PB
Daniel Powner | Head of Adults Learming Disabilities, Autism & Mental Health | daniel.powner@oldham.gov.uk | LIP PB
Debra Woodruff | Head, Oldham College | debra.woodruff@oldham.ac.uk | LIP PB
Elaine Robinson | Service Manager, SENDIASS | elaine@point-send.co.uk | LIP PB
Gavin Lyons | Executive Headteacher, Newbridge School | glyons@newbridgegroup.org | LIP PB
Gerard Jones | Managing Director Children’s Services, OMBC | gerard.jones@oldham.gov.uk | LIP PB
Heather Martin-Netherwood | Associate Director, Children’s Community Services, Northern Care Alliance (NCA) | heather.martinnetherwood@nca.nhs.uk | LIP PB
Jannette Olsen | Universal Health Services, Bridgewater | janette.olsen@nhs.net | LIP PB
Jodie Barber | Head of Service, Youth Service and Outdoor & Environmental Education Service, OMBC | jodie.barber@oldham.gov.uk | LIP PB
Karen Bates | SENCo, Oldham 6th Form College | kbs@osfc.ac.uk | LIP PB
Karen Maneely | CAMHS, MH & Specialist Services, Pennine Care | karen.maneely@nhs.net | LIP PB
Karen Worthington | Universal Health Services, Bridgewater | karen.titchen@nhs.net | LIP PB
Karl Newell | CEO, Crompton House School & Multi Academy Trust | k.newell@cromptonhouse.org | LIP PB
Mark Crilly | Oldham Sixth Form College | MCY@osfc.ac.uk | LIP PB
Martine Lewis | Head of Service, Disabled Children’s’ Team, OMBC | martine.lewis@oldham.gov.uk | LIP PB
Matthew Bulmer | Director of Education, Skills & Early Years, OMBC | matthew.bulmer@oldham.gov.uk | LIP PB
Nathan Wright | Young People's Representative, Barrier Breakers | chris.lewis@oldham.gov.uk | LIP PB
Nick Whitbread | Assistant Director, Social Work Services, OMBC | Nick.whitbread@oldham.gov.uk | LIP PB
Paula Green | Head of Service, SEND and Inclusion, OMBC | paula.green@oldham.gov.uk | LIP PB
Paula Healey | Head of Early Years, OMBC | paula.healey@oldham.gov.uk | LIP PB
Rebecca Fletcher | Director of Public Health, OMBC | rebecca.fletcher@oldham.gov.uk | LIP PB
Victoria Harold | Principal Educational Psychologist & Preventative Lead, OMBC | victoria.harold@oldham.gov.uk | LIP PB
5: Early Identification & Intervention Partnership
Gavin Lyons: Chair | Executive Headteacher, Newbridge School | glyons@newbridgegroup.org | EI&I PG
Alison Bearn: 2nd Chair | Senior Educational Psychologist, OMBC | alison.bearn@oldham.gov.uk | EI&I PG
Agnes Leopald-James | Assistant Director, Childrens Community Nursing, NCA | agnes.leopold-james@nca.nhs.uk | EI&I PG
Ailsa Robinson | SEND Advisory Teacher, OMBC | ailsa.robinson@oldham.gov.uk | EI&I PG
Andrea Atkinson | Headteacher - Royton and Crompton E-ACT Academy | Andrea Atkinson <andrea.atkinson@rca.e-act.org.uk> | EI&I PG
Andrea Greenwood | Oldham Parent Carer Forum Development Manager, POINT | andrea@point-send.co.uk | EI&I PG
Ashleigh Inman | Deputy Headteacher, Bare Trees Primary School | a.inman@baretreesprimary.com | EI&I PG
Beverley O'Neill | Headteacher, Blackshaw Lane Primary School | beverley.o'neill@blackshaw-lane.oldham.sch.uk | EI&I PG
Emma Dewar | Senior Advisory Teacher, OMBC | emma.dewar@oldham.gov.uk | EI&I PG
Emmett Patel | Head of Primary Outreach Service, Kingsland PRU & SLC | e.patel@kingslandschool.org | EI&I PG
Hilary Cook | Senior Director of Inclusion & NW NASEN Rep, North Chadderton School | HCook@northchadderton.oldham.sch.uk | EI&I PG
Hilary Henderson | Headteacher, St Paul’s C E Primary School & Director, Oldham Learning Board | hilary.henderson@stpauls.oldham.sch.uk | EI&I PG
Holly Richards | Highly Specialist Speech and Language Therapist, Better Communication Team, OMBC | Holly Richards <Holly.Richards@oldham.gov.uk> | EI&I PG
Jennifer Rawlins | SEND Nurse | jennifer.rawlins@nca.nhs.uk | EI&I PG
Katie Dallender | Director of Partnerships & East Manchester Teaching School Hub | kdallender@eastmanchesterteachinghub.com | EI&I PG
Natalie Kennerley | Deputy Headteacher (Quality of Education, Teaching & Learning & SEND), The Oldham Academy North | natalie.kennerley@toan.e-act.org.uk | EI&I PG
Sarah Nicholson | SENCO, Waterhead Academy | s.nicholson@waterheadacademy.co.uk | EI&I PG
Sonja Jones | Right Start Early Years Lead Practitioner for Early Years Education and Learning | sonja.jones@nca.nhs.uk | EI&I PG
6: Joint Commissioning & Sufficiency Partnership
Steve Larking Chair | Associate Director: Children and Young People (Transformation), Integrated Care Partnership (Oldham) | s.larking@nhs.net | JC&SUFF
Andrea Weir: 2nd Chair | Senior Commissioning & Partnerships Manager, OMBC | andrea.weir@oldham.gov.uk | JC&SUFF
Amber Burton | Assistant Director, SEND & Inclusion, OMBC | amber.burton@oldham.gov.uk | JC&SUFF
Andrea Greenwood | Oldham Parent Carer Forum Development Manager, POINT | andrea@point-send.co.uk | JC&SUFF
Angela Welsh | Senior Commissioning Business Partner, NHS Greater Manchester Integrated Care | a.welsh@nhs.net | JC&SUFF
Daniel Powner | Head of Adults Learming Disabilities, Autism & Mental Health | daniel.powner@oldham.gov.uk | JC&SUFF
Heather Martin-Netherwood | Associate Director, Children’s Community Services, Northern Care Alliance (NCA) | heather.martinnetherwood@nca.nhs.uk | JC&SUFF
Paula Green: | Head of Service, SEND and Inclusion, OMBC | paula.green@oldham.gov.uk | JC&SUFF
Amaara Khan | Directorate Manager Oldham Integrated Children’s Community Services Ages 0 - 19 | amaara.khan@nca.nhs.uk | JC&SUFF
Martine Lewis | Head of Service, Disabled Children’s’ Team, OMBC | martine.lewis@oldham.gov.uk | JC&SUFF
7: Preparation for Adulthood Steering Group
Charlotte Walker: Chair | Assistant Director, ASC Reform and Improvement | charlotte.walker@oldham.gov.uk | PfA SG
Amanda Youlden: 2nd Chair | Post 16 Lead, OMBC | amanda.youlden@oldham.gov.uk | PfA SG
Amber Burton: | Assistant Director, SEND & Inclusion, OMBC | amber.burton@oldham.gov.uk | PfA SG
Chris Lewis | Youth Service OMBC | Chris.Lewis@oldham.gov.uk | PfA SG
Dawn Price | Adults Social Care, OMBC | dawn.price@oldham.gov.uk | PfA SG
Donna Marshall | Director of Education & Careers Guidance, Positive Steps | donnamarshall@positive-steps.org.uk | PfA SG
Elaine Ratherham | Educational Psychologist, OMBC | elaine.ratheram@oldham.gov.uk | PfA SG
Gary McDermott | After Care Team, OMBC | Gary.McDermott@oldham.gov.uk | PfA SG
Hilary Cook | Senior Director Achievement Support, North Chadderton School, The Oak Trust | HCook@northchadderton.oldham.sch.uk | PfA SG
James Ogborn | Employer Engagement Officer, Get Oldham Working, OMBC | james.ogborne@oldham.gov.uk | PfA SG
John King | PCFT for Learning Disabilities | johnking@nhs.net | PfA SG
Karen Bates | SENCo, Oldham 6th Form College | kbs@osfc.ac.uk | PfA SG
Martine Lewis | Head of Service, Disabled Children’s’ Team, OMBC | martine.lewis@oldham.gov.uk | PfA SG
Milly Smith | ALS Team Leader, Oldham College | milly.smith@oldham.ac.uk | PfA SG
Stephanie Firth | ALS Manager, Oldham College | stephanie.firth@oldham.ac.uk | PfA SG
8: Speech, Languae & Communication Needs Steering Group
Steve Larking: Chair | Associate Director: Children and Young People (Transformation), Integrated Care Partnership (Oldham) | s.larking@nhs.net | SLCN SG
Amber Burton: 2nd Chair | Assistant Director, SEND & Inclusion, OMBC | amber.burton@oldham.gov.uk | SLCN SG
Adam Shipp | Clinical Director, Community Paediatrics, Northern Care Alliance (NCA) | adam.shipp@nca.nhs.uk | SLCN SG
Amaara Khan | Directorate Manager Oldham Integrated Children’s Community Services Ages 0 - 19 | amaara.khan@nca.nhs.uk | SLCN SG
Andrea Greenwood | Oldham Parent Carer Forum Development Manager, POINT | andrea@point-send.co.uk | SLCN SG
Angela Welsh | Senior Commissioning Business Partner, NHS Greater Manchester Integrated Care | a.welsh@nhs.net | SLCN SG
Debbie Burton | Educational Psychologist, OMBC | debbie.burton@oldham.gov.uk | SLCN SG
Emma Dewar | Senior Advisory Teacher, OMBC | emma.dewar@oldham.gov.uk | SLCN SG
Heather Martin-Netherwood | Associate Director, Children’s Community Services, Northern Care Alliance (NCA) | heather.martinnetherwood@nca.nhs.uk | SLCN SG
Jenny Whitehead | Northern Care Alliance (NCA) | jennifer.whitehead2@nhs.net | SLCN SG
Paula Healey | Head of Early Years, OMBC | paula.healey@oldham.gov.uk | SLCN SG
Philip Wadsworth | Senior Educational Psychologist, OMBC | Philip.Wadsworth@oldham.gov.uk | SLCN SG
9: Children & Young People's Mental Health Steering Group
Steve Larking:Chair | Associate Director: Children and Young People (Transformation), Integrated Care Partnership (Oldham) | s.larking@nhs.net | MH SG
Vicki Harold: 2nd Chair | Principal Educational Psychologist & Preventative Lead, OMBC | victoria.harold@oldham.gov.uk | MH SG
Andrea Greenwood | Oldham Parent Carer Forum Development Manager, POINT | andrea@point-send.co.uk | MH SG
Angela Welsh | Senior Commissioning Business Partner, NHS Greater Manchester Integrated Care | a.welsh@nhs.net | MH SG
Christine Ihenacho | Educational Psychologist, OMBC | christine.ihenacho@oldham.gov.uk | MH SG
Emmett patel | Head of Primary Outreach Service, Kingsland PRU & SLC | emmett.patel@oldham.gov.uk | MH SG
Gary Flanagan | Strategic Lead for Mental Health Crisis & Liaison (GM) & Mental Health and Learning Disability (Oldham) | gary.flanagan@nhs.net | MH SG
Grace Walsh | CAMHS School Link Worker | a.welsh@nhs.net | MH SG