## Steering Group Ownership
Date initiated:
Name of Service(s):
Role | Name | Organisaiton | Job title
Chair
NHS Lead
Commmissioning Lead
NHS Quality Lead
Procurment lead
Council Client Support Services rep (Ops)
Relevant Council Head of Service
Council Quality and Compliance
Care Quality Commission
Communication Lead
Finance Lead
Council legal represtative
MioCare representation
Information Governance representation
Other Members
To receive updates but not attend

## Steering Group Actions
Date updated |  |  | Responsibility - to be completed by Steering Group
Initials of responsible Officer
Theme | No. | Action | Council | NHS | Provider | Progress | Risks | Status
Provider Failure Steering Group | 1.1 | Assemble Team and plan the work
| 1.2 | Appoint Lead Officer(s) Note: Head of Service for provider within CMM (E.g. WAA or OAA) and Head of Operations are joint lead for the Provider Failure Process. Where there is an absence at Head of Service level within CMM, Head of Operations becomes lead for appropriate cover and escalation for decision making.
1.3
1.4
Initial work / clarification | 2.1 | Establish timescales for failure(s)
| 2.2 | Establish number of Service Users affected, and User category, and who funds them
| 2.3 | Seek an up to date list of other Providers with potential capacity (liaise with CQC as necessary)
| 2.4 | Consult adjacent Local Authority officers as necessary
| 2.5 | Establish tasks and timescales and allocate them
Project manager overseeing reviews of residents
| 2.6 | Allocate lead workers and equipment & management support requirements
| 2.7 | Consider equipment issues: mattresses, furniture, hoists, packing boxes etc. Who owns it? Can it be transferred? Does any belong to ICES?
| 2.8 | Arrange a meeting with Owners/other relevant parties
| 2.9 | Clarify if the service provider has a Business Continuity Plan in place as part of the contractual arrangements that can be used. In the current circumstances, is it still viable?
| 2.1 | Agree when and how service users and carers are informed (and by whom) of the need to change provider at an early stage.
| 2.11 | Check that the Owner allows free and open access by professionals to the service over the relocation period
| 2.12 | Agree the ‘need to know’ information that should be shared with other parties e.g. care professionals; GP; NHS urgent care lead; other potential Care Providers
[Note that even though a Provider may be considered at serious risk of ‘business failure’, their affairs are still covered by the principle of ‘commercial confidentiality’, and care should be taken that without the Provider’s agreement specific information is not disclosed to third parties which might actually precipitate the business’s final demise].
| 2.13 | Formal scripts to be developed with the lead
Communications Department for: -
• staff working with service users and relatives
• provider staff
• press Clear and concise comms to be prepared and agreed, and to be shared across all those involved at the same time for consistency.
| 2.14 | At the time of a potential failure, investigate the potential of staff or voluntary groups to facilitate service users/carers visiting other provision
| 2.15 | Identify key Care Provider Management staff to be involved and consider Consider when they should be included in meetings and when not.
| 2.17 | Identify site(s) for offsite meetings for Management Team/Care staff if required
| 2.18 | Other agencies to be involved?
| 2.19 | Follow Serious Incident (formerly known as Serious Untoward Incident) procedure or, for OMBC, business continuity and contingency plan. In addition, consideration to be given through the Safeguarding Adults Board (including NHS England as appropriate) as to whether a Safeguarding Adults Review would be commissioned.
| 2.2 | Consider whether failure of this Provision is likely to have a have a significant impact on overall local market supply for this type of service.
| 2.21 | Ensure all officers have considered the impact of the failure process upon other workstreams and escalated as necessary to line manager
| 2.22 | Identify agency to provide an administrative lead to collate all records
| 2.23 | Clarify, with legal representatives, likelihood of TUPE implications and factor this in to negotiations with current and future service providers
| 2.24 | Consider any immediate detrimental impact on providers staff, that may affect continuity of the service in the short term. Consider how they might be supported, eg through welfare payments etc.
Service Users | 3.1 | Assemble an accurate list of all service users and their needs – and confirm numbers with provider. Also any special factors (such as ‘friendship groups’ where it may be desirable to keep people together if possible)
| 3.2 | Confirm where responsibility lies for assessing any self funding or out of area service users
| 3.3 | Check current Registration category
| 3.4 | Assess service users to identify possible change in need or category of care
| 3.5 | Check if any very frail people and those nearing end of life need exceptional arrangements
| 3.6 | Identify service users wishing to change provision/move sooner rather than later
| 3.7 | Identify service users who should be assessed early in the project work due to their predisposition to stress, anxiety or complexity, or for other factors
| 3.8 | Two-stage Assessments of service user’s capacity to make decisions about accommodation move where mental capacity is identified to be at issue, Accompanying record of Best Interests decision making process to be made . IMCA’s appointed for those lacking family/friends.
| 3.9 | Identify need for generic advocacy to support transfer.
| 3.1 | Identify service users with active ‘Deprivation of Liberty’ (DOL) authorisations and ensure the provider as Managing Authority refers all those affected to the DOLs Team for new assessment on a standard authorisation request or urgent request, depending on the speed of the anticipated move. Contact IMCA and Paid Representatives as appropriate.
| 3.11 | Identify Service Users with ‘Health and Welfare Deputies’, and those with ‘Lasting Powers of Attorney’ for Health and Welfare decisions, and ensure contact is made with the relevant parties.
Financial Responsibilities | 4.1 | Ensure managers have the ability to commit all resources to the failure process including financial as well as staffing
| 4.2 | Any out of borough funded service users? Make external commissioners aware of situation, and confirm whether they wish the Steering Group to act on their behalf to relocate service users
| 4.3 | Identify OMBC funded service users, and identify any Section 117 MHA funded residents in particular.
| 4.4 | Identify NHS-funded service users
| 4.5 | Identify whether there are any private self-funded service users and who will take responsibility for their care. Check capacity and their representation (see 3.8. above)
| 4.6 | Identify any remaining service users who are funded by the Department of Work and Pensions or have ‘Preserved Rights’
| 4.7 | Check current fee level being paid
| 4.8 | Investigate cost of potential new provision
| 4.9 | Take a legal view and response, on the period of contract payment/termination issues etc
| 4.1 | Consider issues such as accumulated personal allowance, fees already paid and owing, petty cash etc
| 4.11 | Identify service users with Deputyship in relation to financial affairs, all Enduring Powers of Attorney and all those with Lasting Powers of Attorney for Property & Affairs. Contact relevant parties and ensure records of their involvement are made, particularly in relation to any changed cost to new placements.
Advocacy / family members | 5.1 | Ascertain the list of names, addresses and telephone numbers
| 5.2 | Identify carers who may themselves have special factors to consider – own health, out of area etc
| 5.3 | Seek fullest involvement of relatives/’significant others’ in the relocation process
| 5.4 | Consider necessity for commissioning advocacy for carers affected (but bear in mind resources implications before proceeding)
| 5.5 | Consider and where necessary undertake carers assessments
Consultation / Information Management | 6.1 | To ensure the process runs smoothly it is essential that all groups are consulted:
Service Users
*Care Staff
Families/representatives
Portfolio holders/councillors in relevant ward
Public/press, via Communications lead
Appropriate internal staff all agencies *Staff to be formally informed either before or after families are informed but on the same day going forward.
| 6.2 | A careful balance will need to be struck so that the existing difficulties of the situation and/or the timescales are not exacerbated
| 6.3 | Ensure Residents meetings are arranged with appropriate levels of management representation
| 6.4 | Ensure Relatives meetings are arranged with appropriate levels of management representation
| 6.5 | Ensure clarity of roles for each agency in meetings with residents, relatives and staff
Relocation (if decision is made to close) | 7.1 | Re-assessment of service users and adequate resource requirements to complete
| 7.2 | Check choice (s) of area/services available that are compatible with service user need/category with resident/carer. CMM to support workers with providing more assurance to families around homes that are CQC rated ‘Requires Improvement’ to give a better understanding of the home.
| 7.3 | Maximise resident/carer ability to make an informed choice about compatible area/services/Homes available, in adherence to the principles of the Mental Capacity Act 2005
| 7.4 | Are there friendships between citizens that need to be maintained?
| 7.5 | Ensure new provider is registered for the category of care required and can meet needs
| 7.6 | Liaise with CQC, NHS, OMBC staff to ensure there are no concerns about the Care Provider
| 7.7 | Offer opportunity for service user/carer to view/visit/trial visit Care Provider
| 7.8 | Seek care staff help to inform/visit potential provision with service user where applicable
| 7.9 | Decision by service user/carer on new provision and date to move
| 7.1 | Help of care staff to take or escort citizen to potential new providers on placement?
| 7.11 | Arrange schedule transport to new provision, in and out of county e.g. car/minibus/ambulance – identify cost and who pays CMM to hold a ring around transport and ensure each social worker is buddied with a CMM worker to liaise with regarding transport requirements. Consideration to be made if there is no transport available then moves cannot take place.
| 7.12 | Consideration of equipment issues, and arrangements for its transfer and installation (see also 2.7 above)
| 7.13 | Ensure service users are accompanied by someone familiar on the day of the move, including carers if possible
| 7.14 | Use current care staff to the fullest; passing on their knowledge of service users to new providers, escorting, transporting etc
| 7.15 | Staff handover to new providers – verbal and written. Care summaries, including care plan that details health and social care needs
| 7.16 | Respect care staff friendships with residents and likely concerns for their future welfare. Find opportunities for current care Staff to verbally discuss service users care needs summary with receiving care Staff, where appropriate
| 7.17 | Maintain a log of decisions and movement of service users
| 7.18 | Move service at their own pace/convenience as far as possible.
| 7.19 | Establish a programme of reviews and resource implications to ensure service users well-being after the move. Establish a Team if required.
| 7.2 | Service users medications and treatment details to transfer with them to receiving provider
| 7.21 | Particular attention to be made to ensure correct identification of relocated service users
| 7.22 | Any changes of GP and new provision to be recorded in all appropriate systems of all necessary organisations involved
| 7.23 | Placements made out of borough should be notified to the receiving NHS/Local Authority
| 7.24 | Provider service user information/case files/summaries/transfer with service users where possible or copies made and transferred
| 7.25 | Consider how many family members/friends might visit the resident in the new care provision; can we assist them to do so?
| 7.26 | Notify Department of Work and Pensions of change of Home
| 7.27 | Liaise closely with legal, Commissioning and Procurement teams to ensure new contracts are issued and old contracts terminated
| 7.28 | Consider whether moves should be arranged to coincide with the moving of other service users or spread over more than a week (if time is available)
| 7.29 | Consider the desirability of temporary/second moves
| 7.3 | Ensure arrangements are in place for safe removal/storage/archiving/destruction of any remaining records. Ensure that records are kept safe and disposed of securely and safely. All records need to be in one place as we have a duty to oversee them although there’s no legislation to say that historical records must be taken by OMBC. There is also no duty that OMBC must look after records as the owners can keep them if they want to, but must we must be assured they’re kept safe or will be disposed of correctly.
Quality Assurance | 8.1 | Ensure there is an effective process for recording and resolving complaints and disputes, and that it is widely understood and universally applied between the ‘interested agencies’.
| 8.2 | Conduct a debrief after every incident to identify good practice, lessons identified and further actions to be taken
| 8.3 | Quality Assurance position statement required - linked to the most recent Quality Improvement Plan
Record keeping | 9.1 | Maintain a record of meetings, decisions made. For maintaining meeting minutes/notes, consider potential to have them recorded so could be transcribed at a later date subject to guidance.
| 9.2 | Designate an administrative lead to collate all records
| 9.4 | Service User outcomes should be recorded, particularly with regard to their health and emotional well-being
| 9.5 | Maintain a risk log that is reviewed throughout the failure process
Lessons learnt | 10.1 | All agencies should participate in a Review of the process once the procedure is completed. The outcome of this de-brief should be to identify Recommendations for future inter-agency learning, including policy, procedure and practical guidance.
| 10.2 | The Review should produce a Report and Recommendations to be submitted to the relevant groups and management levels within each agency, including the Safeguarding Adults Board.

## Emergency Oversight Plan
ITEM | ACTION | LEAD | DEADLINE
Emergency response group established
MA Risk Management Plan
Comms
Provider failure plan in place
Agreement for additional agency staff
Financial oversight of the cost to the council to managing provider failure
Plan for reviewing residents' needs

## Residents
Name | Name | Mosiac ID | Broadcare ID | Age | Next of Kin | Lasting Poower of Attourney H&W / H&W Deputies in place? | Funding Authority | NHS Funding | S.117? | Review Allocated to | Team open to | Review Status | Existing DOLs Arrangements | Best interest Decision | Capacity Assessment | Is an Independent Advocate required? | Safeguarding | Friendship Groups to consider for onward move? | Preferred locations/homes | Quality / Safegaurding concerns in relation to prospective homes | Visits to prospective homes | Planned location of move (note if out of borough notificy host authority) | Date move due | Testing | Support required to move resident (physical and emotional) | Will support be required for family to visit in new placement? | Support required to move possessions | Equipment required | Equipment delivery due | Financial Power of Attourney / Deputies? | Funding arrangement | Has new contract been set up? | Has old contract been closed down? | Top up fee position | Client finance assessment | Letter sent | Is anyone in the family a carer for the resident? (if so refer to checklist for supplimentary questions | Handover informaton prepared by XXXX | Medication and treatment passed to new provider | All relevent service user files passed to new provider | Move status | Any changes of GP completed | Post move follow up feedback
Dianne Buckley
Roland Barry Galbraith
Brenda Gilbert
Stephen Harland
Barry Haseldin
Trevor Howard
James Howarth
June Muller
Sheila Whitehead
Elizabeth Graham
John Webster
Lorraine Armitage – Tameside
Anthony Hands- Tameside MH
Pauline Burns - Rochdale

## Lessons logged
Failing identified | Service responsible